## OS
WORKING GROUPS MONTHLY ACTIONS |  |  | Nov | Nov Meeting
Part complete
WORKING GROUP: |  | OPEN SPACES |  | Complete
TEAM: |  | E.Bell, A. Marr, S Rimmington, D. Parris |  | Outstanding
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
Recreation Ground - Play and sports equipment, Concrete roundels,
Area behind Medway Inn, CCTV area |  |  | Naval Green - Maintenance of Furniture.
Wouldham Common - Fly Tipping, Litter Picking |  |  | Village Green - Maintenance of Furniture.
Grass Cutting - Ensure contract is adhered to. |  |  | Allotments - Liaise with Allotment Association
Develop and progress any special projects identified in the precept
To develop, support and monitor Risk Assessments in liaison with H&S
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | NEXT STEPS/ COMPLETE/RESULT
Lease for G West | TM | Draft lease written | Lease agreed | Meet with Mr West to sign lease and agree works. He also needs to re-site roundel again.
Wouldham Common |  | Signage | Signs collected | Put up
New play equipment | EB/TM | Item ordered | Site checked by contractor as acceptable | Installation due in January 2023
grass cutting areas | EB | Contract update | Final cut done Nov 22 | monitor
Vandalised benches | EB | how much can be spent | Agreed to put on hold until works on the park have been completed. SB to find out prices of metal benches similar to those on the esplanade | On Hold
Signage on Rec | DP | AB and SR to re-site car park rules sign | 3 'rules' signs received | Needs installation with No Horses sign
Sports England Audit | TM | Audit required for Sports England registration of the rec. | Changed site into to: 'Site also has basketball hoop. (No bike stands on site but ample fencing suitable for chaining bikes). Height barrier restrictions for entry into the car park. All organised sports must have prior agreement of the Parish Council' | Complete next due Nov '23
Repair work to play equipment in Rec | TM | See H & S
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL:

## RFL
WORKING GROUPS MONTHLY ACTIONS |  |  | Nov | Nov Meeting
Part complete
WORKING GROUP: |  | ROADS, FOOTPATHS & LIGHTING |  | Complete
TEAM: |  | A. Marr, S. Buchanan, M. Savaryn, A McDermott |  | Outstanding
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
Notify relevant authorities/companies of potholes, damaged road furniture, fly tipping, and signage.
Monitor overgrown vegetation, safe pavement surfaces and report as necessary.
Report lights not working - electric equipment, any lights that have vegetation on them either causing safety issues or blocking out the light.
Village Car Park and pathway |  | monitor condition and signage
Special Projects: | develop and progress any special projects identified in the precept
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | NEXT STEPS COMPLETE/RESULT
lights in Oldfield Drive | AM | Reported that bulb has now blown
car park lights | EB | Passed to RFL to research
Recreation Pathway Lights | EB | RFL to reseach solar bollards
Dropped gully on High Street | TM | Reported to KCC | Spoke to KCC who are looking at all the dropped gullys on the High Street. Will need to do a road closure. | Complete, but letter of complaint to be sent to Southern Water
Water leak 55 High Street | DP | Reported to KCC | Asked KCC to do at the same time as the gullies. | As above
One Way Trial |  | New design agreed | Joint meeting held. Trial to run alongside No right turns into Scarborough Lane and Church Street | Due to start in March '23
Light in Scarborough Lane | TM | Burham PC want to take this off their inventory | Need to arrange for fuse to be removed. But need to confirm with BPC which light. | Arranged with contractor 7/11. Chased 21/11
White lines in car park | EB/TM | TM met with potential contractor to quote for re-lining outside of carpark | This will give an additional 8 spaces to giving 30 spaces for residents only. | 1 quote received @£1235
Blocked drain and flooding around Trafalgar/Nelson |  | Reported to KCC Ref: 660406 | Advised by KCC that the Southern Water system is not sufficient for heavy rain | Continue to monitor and report. Resident complained to KCC
pothole outside 177 | EB | KCC ref 661833 | 14 days max | Complete.
loose cable 180 | EB | openreach ndoexe02 |  | Complete
Resident Complaint about parking on grass verge in Nelson | TM | Ownership checked, but not sure of any convenant | KCC made site visit and photo has been forwarded. | Resident reported to the company vehicle owner. Vehicle is not longer parking there.
Salt Bin Levels | AM | KCC have asked if we need any salt | AM has volunteered, but needs to identify where the bins are.
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL:

## VH
WORKING GROUPS MONTHLY ACTIONS |  |  | Nov | Nov Meeting
Part complete
WORKING GROUP: |  | VILLAGE HALL |  | Complete
TEAM: |  | A. Marr, S. Buchanan, D. Parris |  | Outstanding
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
To plan for the ongoing development with the VH Charity, making recommendations as appropriate
Oversee and agree the terms and conditions of use of the facilities
Oversee and agree the fees relating to the hire of the facilities
Ensure that regular risk assessments and health and safety checks are made in line with current legislation
Ensure the provision of safe and well-maintained facilities for the community use.
Ensure Governing/Deed of Trust document is adhered to
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | COMPLETE/RESULT
Tidy front garden of Village Hall | EB | Grass Cut | Possible 5th August | Complete/ongoing
Governance/Transfer | TM | Sent requests for quotations to specialist solicitors | Chased quotation from Furley Page | Quote for 3-5k received
Rear Fire exit blocked | TM | Letters written to residents. No feedback received | Only 1 fire exit is legaly required for building. Evacuation plan to be updated | Evacuation plan changed.
Major crack in toilet block (structural?) | TM | Claim reference 27220000430. | Insurance will only pay for the crack to be filled, the wall to be braced and decorated. Opinion is this will not exceed the excess. | Suggest discontinuing with claim.
External Painting | AM | Local volunteer has agreed to paint the front of the Hall
Accessible toilet | AM | Potential contractors attended to quote for works | New plans agreed with Committee. Trustees to get quotes
Leak in roof and ceiling | TM | Leak in roof has caused the ceiling to bulge and in danger of collapse | Groups cancelled for w/c 21/11. Investigations show a large amount of debris sitting on the ceiling, the front of the building needs re-pointing and gullies/gutters need clearing. Remedial works to be done by 27/11 at a cost of £1350 from the VH charity. | Work completed 27/11 Groups back 28/11
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL:

## H&S
WORKING GROUPS MONTHLY ACTIONS |  |  | Nov | Dec Meeting
WORKING GROUP: |  | H & S
TEAM: |  | S. Rimmington, D. Parris, A. McDermott
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
Monitor the Councils compliance with relevant legislation and progress towards best practice in health and safety including 1974 Health & Safety at Work Act
To ensure the Council’s Health and Safety Policy is implemented, monitored, developed, communicated effectively, reviewed and amended as required.
To ensure suitable and sufficient funds, people, materials and equipment are provided to meet all health and safety requirements
Ensure adequate insurance cover is provided and renewed
Ensure any accidents, ill health and 'near miss’s are recorded, investigated and reported where necessary
Ensure any safety issues raised are thoroughly investigated and, when necessary, further effective controls implemented
Ensure contractors engaged are reputable, can demonstrate a good health and safety records and are made aware of relevant local health and safety rules and procedures
To develop an emergency plan/disaster recovery plan involving other partners/officials where necessary and assigning a designated competent person in charge of the planning and control measures for situations involving imminent danger
Develop flood risk planning in conjunction with (h)
Develop, monitor and review risk assessments linking with the relevant committee.
Ensure checks of capital equipment and assets are made and any remedial actions taken
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | NEXT STEPS, COMPLETE/RESULT
Review H&S for the VH | TM | Started to compile a H & S File | Requested RA's from regular users | Received from Brownies
Remedial work on ROSPA rep | TM | Quotes sought for remedial work | Emergency works ordered | Works started 14/11 awaiting a replacement ring as unable to repair.
Gate to play area in Rec not closing properly | TM | MS to look at re-aligning | Playground replair company realigned post and adjusted setting | complete.
Non closing gate at the top of the Rec | ? | Need to look at a 'soft' spring to enable self closing.
Fire Exits at the VH | TM | Electrician advised only one exit is needed for the size of the Hall even if others could be used in a emergency. | 1.Clerk to update evacuation plan to use the front door. 2.Clerk to check number of exits required for nurseries | 1. Done 2. Checked with Early Years. It only states Fire RA needs to be considered and exit identified and free from blockages
Emergency lights for VH | AM | Works arranged to update fire exit signs to meet current legislation. Emergency light to also be fitted to toilet block | Completed 25/10 | Once work is completed, ask Fire Brigade to visit
Defibrillator | TM | Investigations on where to put the spare one. | Contacted Church to find out costs and who will do it. | Churches electrician is going to look at the cabinet on the shop and see if a facaulty is required.
Defibrillator Village Hall | TM | Monthly Check | Check battery and any use | Checked 18/11
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL:

## Planning
WORKING GROUPS MONTHLY ACTIONS |  |  | Nov | Dec Meeting
WORKING GROUP: |  | PLANNING
TEAM: |  | E.Bell, A. Baker, A. McDermott, S. Buchanan
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
To make representations to the Local Planning Authority on applications for planning permission which have been notified to the Council
To make representations in respect of appeals against the refusal of planning permission
To identify and make representations to the relevant authorities in respect of enforcement action or any matters considered to be breaches of planning regulations;
The Working Group will consider each application on its merits.
All Parish Council members are notified of applications within 3 working days of Parish meeting and may be viewed via the Tonbridge and Malling Planning Portal. All Committee decisions will be recorded in the Parish Council minutes.
The Working Group, whilst considering the views of residents and other interested parties, is not duty bound to pass on these views when making its decision, they may submit a budget to the Council as part of the Council’s overall budget process.
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | COMPLETE/ RESULT
22/02413/FL 3 Keepers Cottage Lane, Single Storey extension. | EB | Checked against planning regs | Comment to check any covenants and inform Trenport. And confirm neighbours consulted
22/01119/RM Phase 5 Parcels 3A And 3B Worrall Drive. Reserved Matters application pursuant to outline application ref TM/15/01485/OAE relating to appearance, layout, landscaping and scale. |  |  |  | APPROVED
Downs Farm Area 3 meeting | EB | Area 3 Site meeting took place 2/11 | Area 3 Committee agreed to refuse | Refused
RESOLUTIONS TO FULL COUNCIL:

## F&A
WORKING GROUPS MONTHLY ACTIONS |  |  | Nov
WORKING GROUP: |  | FINANCE
TEAM: |  | E.Bell, A. Baker, S. Rimmington
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
To consider the quarterly budget monitoring reports provided by the Clerk with any recommendations being put to the Council.
To consider the annual budget and the annual precept and take recommendations and comments to the full council.
All Council members will be provided with a list of payments for approval prior to each Council meeting. Any payment can be queried at the Council meetings. If necessary, a vote be taken to authorise payment with the Chairman of the Council Meeting having the casting vote when there are equal numbers of votes.
A member of the Committee will sign off the bank statement from the previous month, at each Council meeting.
During each Council meeting, 2 bank signatories, will agree payments for the month.
To monitor staffing in line with the Terms of Reference
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | COMPLETE/RESULT
date of quarterly meeting/ budget review | TM | Dates circulated |  | Held on 25/10
Liz Phillips's appraisal | TM | Appraisal form sent | Appraisal due 31/10 | Complete 31/10
Pay review for precept | TM | Calculations circulated based on NALC increase | To be agreed at finance meeting | Agreed 25/10
SR to be added to signatory list | TM | Raised mandate | awaiting sign off SR | paperwork sent out again
Annual Investment Strategy needed as funds exceed 100k | TM | Write strategy for approval |  | approved 2/11
Budget Setting for 23/24 |  | Initial budget setting complete | Awaiting confirmations from Orchard re charges
FOI Request regarding traffic | TM | Compiling emails re traffic issues and consultation | Contacted IOC and TMBC for guidance
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL: |  | To approve Annual Investment Strategy